## Control Register
Happy Insurance Brokers — Control Register
Bridges Risk Register risks to ISO 27001 Annex A controls and implementation status. As of: August 2026
Control ID | Control | Type | ISO 27001 Ref | Owner | Mitigates Risk(s) | Status | Target Date
AC-001 | Multi-factor authentication (CRM, email, remote access) | Preventive | A.8.5, A.5.15 | IT Manager | R1, R3 | Not Started | 30 days
AC-002 | Strong password policy (enforced via Group Policy) | Preventive | A.5.17 | IT Manager | R3 | Not Started | 30 days
AC-003 | Role-based access control | Preventive | A.5.15, A.8.3 | IT Manager | R1, R3 | Not Started | 60 days
DP-001 | Automated, encrypted, offsite backup with restore testing | Corrective | A.8.13 | IT Manager | R4 | Not Started | 45 days
DP-002 | POPIA data retention & disposal policy and schedule | Preventive | A.5.33, A.8.10 | Compliance Officer | R5 | Not Started | 30 days
DP-003 | Information Officer duties registered | Preventive | A.5.34 | Compliance Officer | R5 | Not Started | 30 days
DP-004 | Full-disk encryption on staff laptops | Preventive | A.8.24, A.7.9 | IT Manager | R8 | Not Started | 45 days
DP-005 | Mobile Device Management (MDM) rollout | Preventive | A.8.1 | IT Manager | R8 | Not Started | 60 days
MW-001 | Endpoint Detection & Response (EDR) deployment | Preventive / Detective | A.8.7 | IT Manager | R2 | Partial | 90 days
MW-002 | Centralized patch management (30-day SLA) | Preventive | A.8.8 | IT Manager | R2 | Not Started | 90 days
CT-001 | CPD/RE5 tracking register with renewal alerts | Detective | - | Compliance Officer | R6 | Not Started | 30 days
CT-002 | Structured product & needs-analysis training programme | Preventive | A.6.3 | Compliance Officer | R7 | Not Started | 60 days
BC-001 | UPS and backup generator installation | Preventive | A.7.11 | Operations Manager | R9 | Not Started | 90 days
BC-002 | Documented and tested Business Continuity Plan | Corrective | A.5.29, A.5.30 | Operations Manager | R9 | Not Started | 90 days
FD-001 | Segregation of duties - claims assessment vs. payment approval | Preventive | A.5.3 | Claims Manager | R10 | Partial | 60 days
FD-002 | Automated transaction monitoring on claims payments | Detective | A.8.16 | Claims Manager | R10 | Not Started | 90 days
VN-001 | Vendor security due-diligence process | Preventive | A.5.19, A.5.20 | Compliance Officer | R11 | Not Started | 60 days
EM-001 | Email authentication (SPF/DKIM/DMARC) | Preventive | A.8.20 | IT Manager | R12 | Not Started | 30 days
EM-002 | Telephonic callback verification for banking detail changes | Preventive | A.5.14 | IT Manager | R12 | Not Started | 30 days
CM-001 | Documented complaints-handling & escalation policy | Preventive / Detective | A.5.24 | Compliance Officer | R13 | Not Started | 30 days
KP-001 | Documented SOPs for key IT and compliance tasks | Preventive | A.5.37 | Compliance Officer | R14 | Not Started | 90 days
KP-002 | Cross-trained deputy compliance resource | Corrective | - | Managing Director | R14 | Not Started | 90 days
IR-001 | Incident Response Policy and Playbook | Corrective / Detective | A.5.24, A.5.26 | Compliance Officer / IT Manager | All (cross-cutting) | Implemented | Complete (Aug 2026)
GV-001 | Risk Appetite Statement approved by Board | Preventive | - | Managing Director | All (cross-cutting) | Implemented | Complete (Aug 2026)
Status Legend: | Implemented | Partial | Planned | Not Started
Note: This register operationalizes the Risk Treatment Plan and ISO 27001 Gap Assessment Remediation Roadmap into individually trackable controls. Status should be updated as each control is implemented and verified; 'Planned' in the underlying data was consolidated into 'Not Started' above for simplicity where no work has yet begun.