## Risk Register
Happy Insurance Brokers — Risk Register
Fictional short-term insurance brokerage (FSP) ¦ FAIS / POPIA / TCF scope ¦ Prepared: August 2026 ¦ Reviewed by: Compliance Officer
Risk ID | Asset | Asset Category | Threat | Vulnerability | Risk Description | Existing Controls | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Rating | Recommended Controls | Control Type | Risk Owner | Framework Reference
R1 | Client CRM (client PII: ID numbers, contact & policy data) | Information / Systems | External attacker – phishing / credential theft | No multi-factor authentication on CRM; limited staff security awareness training | A phishing email exploiting untrained staff could grant unauthorised access to the CRM, exposing client PII and triggering a POPIA breach. | Basic username/password login; annual induction covers POPIA in general terms only | 4 | 5 | 20 | Critical | Enforce MFA on all CRM accounts; deliver quarterly phishing-simulation and security awareness training; enable login/access alerting | Preventive | IT Manager | POPIA s19 (security safeguards); NIST CSF - Protect (PR.AC)
R2 | Policy administration system & file server | Systems | Ransomware | Outdated OS/application patching; no endpoint detection & response (EDR) tool | A ransomware attack exploiting unpatched systems could encrypt policy records, halting claims and new business processing. | Basic antivirus; manual, infrequent patching | 3 | 4 | 12 | High | Implement centralised patch management (30-day SLA); deploy EDR; maintain isolated offline backups tested quarterly | Preventive / Corrective | IT Manager | NIST CSF - Protect (PR.IP) & Recover (RC.RP)
R3 | Staff user accounts (CRM, email, policy system) | Systems | Account compromise / brute force | Weak password policy; shared/generic logins in some branches | Weak credentials could allow an attacker to compromise a staff account and move laterally across client-facing systems. | 8-character minimum password policy, not enforced technically | 3 | 4 | 12 | High | Enforce strong password policy via Active Directory/Group Policy; eliminate shared logins; roll out MFA (shared control with R1) | Preventive | IT Manager | NIST CSF - Protect (PR.AC-1)
R4 | Client policy & claims records (digital) | Information | Hardware failure / fire / theft of server | No offsite or cloud backup; single on-premise server | Loss of the on-premise server without an offsite backup would result in permanent loss of client policy and claims history. | Local backup to an external drive, performed ad hoc | 2 | 5 | 10 | High | Implement automated, encrypted daily backups to a cloud provider; run quarterly restore tests; document a data backup standard | Corrective | IT Manager | ISO 27001 A.8.13 (Backup); POPIA s19
R5 | Client personal information (all systems & paper files) | Information / Regulatory | Regulatory non-compliance (POPIA) | No documented data retention or secure disposal policy; no appointed Information Officer duties formalised | Retaining client data indefinitely without a lawful basis or secure disposal process breaches POPIA's retention limitation condition and exposes the firm to Information Regulator enforcement. | Verbal understanding of POPIA among senior staff; no written policy | 4 | 4 | 16 | Critical | Draft and implement a POPIA data retention & disposal policy; formally register Information Officer duties; conduct a data mapping exercise | Preventive | Compliance Officer | POPIA s14 (retention); Information Regulator guidance
R6 | Advice given to clients (sales & broking staff) | People / Regulatory | Regulatory non-compliance (FAIS) | No formal tracking of RE5 status or Continuous Professional Development (CPD) hours | A representative operating with a lapsed RE5 or incomplete CPD could render advice that is not FAIS-compliant, risking FSCA sanction and client harm. | RE5 checked at hiring only; no ongoing tracking | 3 | 4 | 12 | High | Implement a CPD/RE5 tracking register with renewal alerts; annual internal FAIS compliance audit; supervision sign-off for new advisers | Detective / Preventive | Compliance Officer | FAIS Act (Fit & Proper requirements); FSCA CPD Cycle
R7 | Client sales & advice process | People / Regulatory | Mis-selling / unsuitable advice | Inconsistent product training; no structured needs-analysis process enforced | Inadequately trained consultants recommending unsuitable cover could breach Treating Customers Fairly outcomes and drive complaints or FSCA action. | Informal on-the-job product training | 3 | 3 | 9 | Medium | Structured product & needs-analysis training programme; TCF outcome monitoring via complaints and lapse-rate data; call/quality audits | Preventive / Detective | Compliance Officer | TCF Outcomes 1-6 (FSCA)
R8 | Staff laptops (used off-site by consultants) | Hardware | Theft or loss of device | No full-disk encryption; no mobile device management (MDM); no remote-wipe capability | A stolen, unencrypted laptop containing cached client data would expose PII outside the firm's control with no ability to remotely wipe it. | Laptop login password only | 3 | 4 | 12 | High | Roll out full-disk encryption (BitLocker) and an MDM solution with remote wipe; enforce automatic screen-lock and device registration | Preventive | IT Manager | POPIA s19; ISO 27001 A.8.1
R9 | Office operations & call centre availability | Physical / Systems | Power outage (load shedding) / utility failure | No uninterruptible power supply (UPS) or generator; no documented business continuity plan | Extended power outages could halt claims processing and client communication, breaching service-level commitments and TCF fair-outcome obligations. | Informal manual workarounds; no backup power | 4 | 3 | 12 | High | Install UPS for critical systems and a backup generator; document and test a Business Continuity Plan (BCP) covering outages of 4+ hours | Preventive / Corrective | Operations Manager | ISO 22301 principles; TCF Outcome 5 (service standards)
R10 | Claims payment process | People / Financial | Insider fraud | No segregation of duties between claims assessment and payment approval; limited transaction monitoring | A claims handler could manipulate or approve fraudulent payouts without independent review, resulting in direct financial loss. | Manager spot-checks on an ad hoc basis | 2 | 4 | 8 | Medium | Enforce segregation of duties (assess vs. approve vs. pay); implement automated transaction monitoring and monthly reconciliation review | Preventive / Detective | Claims Manager | Internal control best practice; FAIS Act (operational ability)
R11 | Policy administration SaaS vendor | Third-Party / Systems | Vendor data breach | No formal vendor due-diligence process; contract lacks explicit security/breach-notification clauses | A breach at the third-party SaaS provider hosting policy data would expose client information the firm remains legally accountable for under POPIA. | Standard vendor service agreement, security clauses not reviewed | 2 | 4 | 8 | Medium | Conduct annual vendor security due diligence; add contractual breach-notification and audit-right clauses; consider cyber liability insurance | Preventive | Compliance Officer | POPIA s20-21 (Operator obligations)
R12 | Email system / client payment instructions | Systems / Financial | Business Email Compromise (BEC) / invoice fraud | No email authentication (SPF/DKIM/DMARC); no callback verification for banking-detail changes | A spoofed email requesting a change of banking details could redirect a client premium or claim payout to a fraudster's account. | Staff asked to 'double-check' suspicious emails informally | 3 | 4 | 12 | High | Implement SPF/DKIM/DMARC email authentication; mandate telephonic callback verification for any banking detail change | Preventive | IT Manager | NIST CSF - Protect (PR.DS); industry BEC guidance
R13 | Brand & public reputation | Reputation | Negative publicity / social media complaints | No documented social media or complaints-escalation policy | A mishandled public complaint on social media could escalate reputational damage and attract regulatory attention to underlying service failures. | Complaints handled informally by branch staff | 3 | 2 | 6 | Medium | Implement a documented complaints-handling and social media escalation policy aligned to TCF; assign a designated response owner | Preventive / Detective | Compliance Officer | TCF Outcome 6 (complaints handling)
R14 | Compliance function continuity | People | Key-person unavailability (resignation, illness) | Single Compliance Officer; processes not documented; no deputy or succession plan | The sudden unavailability of the sole Compliance Officer would leave FAIS/POPIA obligations unmonitored, risking regulatory breaches going undetected. | None – single point of failure | 2 | 3 | 6 | Medium | Document key compliance procedures (SOPs); cross-train a deputy compliance resource; formalise a succession plan | Preventive | Managing Director | FAIS Act (Key Individual requirements)
Risk Rating Legend: | Low (1-4) | Medium (5-9) | High (10-15) | Critical (16-25)
Note: Risk Score = Likelihood x Impact (both rated 1-5). Ratings and fills recalculate automatically from Likelihood/Impact inputs.

## Risk Matrix
Happy Insurance Brokers — Risk Matrix (5x5 Heat Map)
Risk IDs plotted by Likelihood (x-axis) and Impact (y-axis) - Risk Score = Likelihood x Impact. Mirrors Risk Register as of August 2026.
| Impact \ Likelihood | 1 Rare | 2 Unlikely | 3 Possible | 4 Likely | 5 Almost Certain
| 5 Severe |  | R4 |  | R1
| 4 Major |  | R10 R11 | R2 R3 R6 R8 R12 | R5
| 3 Moderate |  | R14 | R7 | R9
| 2 Minor |  |  | R13
1 Negligible
Risk ID Key:
| R1 | Client CRM data breach (phishing / no MFA)
| R2 | Ransomware on policy admin system
| R3 | Weak passwords / no MFA - account compromise
| R4 | Loss of data - no offsite backups
| R5 | POPIA non-compliance - no retention/disposal policy
| R6 | FAIS non-compliance - RE5/CPD not tracked
| R7 | TCF breach - mis-selling / inadequate training
| R8 | Theft of unencrypted laptops
| R9 | Load shedding / power outage - no BCP
| R10 | Insider fraud - claims payment manipulation
| R11 | Third-party SaaS vendor breach
| R12 | Business Email Compromise / invoice fraud
| R13 | Reputational risk - social media complaints
| R14 | Key-person risk - single Compliance Officer
Note: R2, R3, R6, R8 and R12 all score Likelihood 3 x Impact 4 = 12 (High) and share one grid cell for space; see Risk Register for individual detail on each.

## ISO 27001 Mapping
Happy Insurance Brokers — ISO/IEC 27001:2022 Annex A Control Mapping
Maps each identified risk to the Annex A:2022 control(s) that treat it. Recommended Controls (Risk Register) are the implementation detail; this sheet shows the framework alignment.
Risk ID | Risk (Summary) | Annex A Theme | Control ID(s) | Control Name(s) | How It Treats the Risk | Implementation Status | Risk Rating
R1 | Client CRM data breach via phishing (no MFA) | Technological | A.8.5, A.5.15 | Secure Authentication; Access Control | MFA and role-based access control directly reduce likelihood of unauthorised CRM access via a compromised credential. | Not Implemented | Critical
R2 | Ransomware on policy admin system / file server | Technological | A.8.7, A.8.13, A.8.8 | Protection Against Malware; Backup; Management of Technical Vulnerabilities | Malware protection and patching reduce the likelihood of infection; tested backups reduce impact by enabling recovery without paying ransom. | Partially Implemented | High
R3 | Account compromise - weak passwords, no MFA | Technological | A.5.17, A.8.5 | Authentication Information; Secure Authentication | Enforced password standards and MFA close the credential-based entry point exploited in account takeover. | Not Implemented | High
R4 | Loss of client data - no offsite backups | Technological | A.8.13 | Backup | Automated, tested offsite/cloud backups ensure data can be restored after hardware failure, fire, or theft. | Not Implemented | High
R5 | POPIA non-compliance - no retention/disposal policy | Organizational | A.5.33, A.5.34, A.8.10 | Protection of Records; Privacy and Protection of PII; Information Deletion | A documented retention schedule and secure disposal process satisfy both ISO record-keeping controls and POPIA's retention-limitation condition. | Not Implemented | Critical
R6 | FAIS non-compliance - RE5/CPD not tracked | People | A.6.3 | Information Security Awareness, Education and Training | A tracked competence/training programme (extended here to RE5/CPD) evidences ongoing fitness of staff providing advice. | Not Implemented | High
R7 | TCF breach - mis-selling / inadequate training | People | A.6.3, A.5.31 | Awareness & Training; Legal, Statutory, Regulatory and Contractual Requirements | Structured product training plus monitoring against regulatory requirements reduces the risk of unsuitable advice reaching clients. | Partially Implemented | Medium
R8 | Theft of unencrypted laptops | Physical | A.7.9, A.8.24 | Security of Assets Off-Premises; Use of Cryptography | Full-disk encryption protects data confidentiality if a device is lost or stolen; asset-handling rules reduce the chance of loss in the first place. | Not Implemented | High
R9 | Load shedding / power outage - no BCP | Organizational | A.5.29, A.5.30, A.7.11 | Information Security During Disruption; ICT Readiness for Business Continuity; Supporting Utilities | A documented BCP plus backup power (UPS/generator) maintains critical operations through planned or unplanned outages. | Not Implemented | High
R10 | Insider fraud - claims payment manipulation | Organizational | A.5.3, A.8.16 | Segregation of Duties; Monitoring Activities | Separating claims assessment from payment approval, backed by transaction monitoring, prevents one individual from originating and approving fraud undetected. | Partially Implemented | Medium
R11 | Third-party SaaS vendor breach | Organizational | A.5.19, A.5.20, A.5.22 | Information Security in Supplier Relationships; Addressing Security in Supplier Agreements; Monitoring of Supplier Services | Due diligence, contractual security clauses, and ongoing monitoring extend the firm's control environment to data held by the vendor. | Not Implemented | Medium
R12 | Business Email Compromise / invoice fraud | Technological | A.8.20, A.5.14 | Networks Security; Information Transfer | Email authentication (SPF/DKIM/DMARC) and a verified transfer process for payment instructions prevent spoofed requests from being actioned. | Not Implemented | High
R13 | Reputational risk - social media complaints | Organizational | A.5.24, A.5.31 | Incident Management Planning and Preparation; Legal, Statutory, Regulatory and Contractual Requirements | A documented complaints/escalation process ensures public complaints are handled consistently and don't compound into a wider incident. | Not Implemented | Medium
R14 | Key-person risk - single Compliance Officer | Organizational | A.5.2, A.5.30 | Information Security Roles and Responsibilities; ICT Readiness for Business Continuity | Documented procedures and a cross-trained deputy ensure compliance oversight continues if the sole Compliance Officer is unavailable. | Not Implemented | Medium
Annex A Theme Legend: | Organizational | People | Physical | Technological
Note: Control references follow ISO/IEC 27001:2022 Annex A (93 controls across four themes: Organizational, People, Physical, Technological). Implementation Status reflects current state before the Risk Treatment Plan is executed; update as controls are implemented and verified.